# Morehead One Senior Care – Critical Path

# PROCUREMENT ACTION ITEMS – HARD DEADLINES

### 1. Electrical Subcontract

- Award by: December 19, 2025

- Submittals due: January 5, 2026

- Release long-lead gear by: January 10, 2026

### 2. Division 8 – Doors, Frames & Hardware (including electrified hardware)

- Award by: December 19, 2025

- Submittals due: January 5, 2026

- Approve by: January 20, 2026

- Release for fabrication: January 21, 2026

- Delivery required on-site by: April 20, 2026

### 3. Storefront / Glazing

- Award by: December 19, 2025

- Submittals due: January 10, 2026

- Delivery required: Early April 2026

### 4. Interior Finishes (drywall, ACT, paint)

- Award by: January 10, 2026

- Material release: February 1, 2026

- Ready for install: May 2026

### 5. Flooring

- Award by: January 31, 2026

- Delivery required: Late May 2026

### 6. Casework

- Award by: January 31, 2026

- Approve shop drawings by: February 15, 2026

- Delivery required: Week of June 15, 2026

### 7. Division 10 (restroom partitions, accessories, signage)

- Award by: February 15, 2026

- Delivery required: Week of June 22, 2026

### 8. Miscellaneous Metals / Handrails

- Award by: February 15, 2026

- Delivery required: June 2026

### 9. PEMB (Already Awarded)

- Shop drawings: Immediate

- Fabrication window: Through Feb 2026

- Delivery required: March 1, 2026

# CRITICAL-PATH CONSTRUCTION DEADLINES

### 1. Sitework

January 5 – January 14, 2026
Must finish on time or it affects foundations.

### 2. Foundations

January 15 – January 28, 2026
Anchor bolt layout must be perfect for PEMB.

### 3. MEP Underground

January 29 – February 11, 2026
Electrical award must happen before this.

### 4. Slab on Grade

February 12 – February 18, 2026
No float here.

### 5. PEMB Erection

March 2 – April 3, 2026
This is a zero-slack activity.
Any delay pushes the entire project.

### 6. Interior Framing

March 30 – April 10, 2026

### 7. MEP Rough-In

April 6 – May 8, 2026
Must complete before drywall.

### 8. Drywall Hang & Finish

May 11 – May 29, 2026

### 9. Paint

June 1 – June 12, 2026

### 10. Flooring

June 1 – June 19, 2026

### 11. ACT Ceilings

June 8 – June 12, 2026

### 12. Doors/Hardware Install

June 15 – June 26, 2026
Electrified hardware MUST be on-site before this.

### 13. Casework Install

June 15 – June 19, 2026

### 14. Division 10 Install

June 22 – June 26, 2026

### 15. Substantial Completion

June 26, 2026

### 16. Punchlist + Final Completion

June 29 – July 3, 2026